## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
As a < type of user >, I want < some goal > so that < some reason >
| Create account | (registerd user) | 3 | yes | 1 | completed
Register user can get discounts in future
Register user can save payment details (card datalis)
|  | (guest user) |  |  | 2 | completed
as a guest user (no discounts / no data saving)
| View Restaurants | (register user) must sign in first to view all restaurants | 5 | yes | 1 | completed
|  | (guest user) can view the restaurants directly | 5 | yes | 2 | completed
| Search Restaurants | all user type can search for all available restaurants | 5 | yes | 3 | completed
|  | all users can search for restaurants that have discounts | 3 | no | 1 | not started
|  | all users can search about specific type of restaurant (indian/italian) | 2 | no | 4 | not started
| View Menu | all users can view the menu | 5 | yes | 1 | completed
| Add to cart | all users can add to cart | 5 | yes | 3 | testing
|  | all users will get notification if the order not completed | 5 | yes | 2 | not started
|  | (registerd user) get 25% discount after the thired order automatically | 5 | yes | 1 | in progress
| Purchase | (register user) pay cash / card | 3 | yes | 4 | completed
|  | (guest user) pay via card only |  |  | 3 | completed
| Restaurant views order | all users can view orders | 5 | yes | 2 | completed
|  | (restaurant owner) can view the order details | 5 | yes | 1 | in progress
| Restaurant marks order as delivered | all users will notice a mark that the order is delivred | 5 | yes | 4 | not started
|  | (restaurant owner) will notice a mark that the order is delived | 5 | yes | 5 | not started